## Brand Rollout
# | Task | Day | Owner / Agent | Category | Dependencies | Status | Notes
1 | Brand Constitution final update (3-layer architecture, taxonomy rule, flywheel, maturity model) | Day 1 | Emily (Brand Steward) | Strategy | - | In Progress | Consolidate all 6 phase decisions
2 | Brand Checklist (single-page, 7-point audit) | Day 1 | Emily + ECHO | Strategy | Constitution | Not Started | Every agent runs before publishing
3 | KPI baseline snapshot (website, LinkedIn, NEXUS, webinar) | Day 1 | Emily + LENS | Analytics | - | Not Started | Day 0 baseline for all 15 metrics
4 | Website hero + nav + services page copy (first draft) | Day 1 | ECHO | Website | Constitution | Not Started | Taxonomy rule: outcomes lead
5 | Website hero + services design mockup | Day 1 | Valentina | Design | Copy draft (ECHO #4) | Not Started | Visual direction for new positioning
6 | Add rollout tasks to master tracker | Day 1 | Emily | Operations | - | Done | This sheet
7 | Website: all core pages copy finalized (hero, services, about, contact, homepage, dropdowns) | Day 2 | ECHO | Website | Day 1 draft | Not Started | Full site copy under new positioning
8 | Website: design implementation of all core pages | Day 2 | Valentina + Akira | Website | Copy final + Day 1 mockup | Not Started | Visual + build
9 | LinkedIn: company page + all partner profiles (headline + About) | Day 2 | ECHO + Carl | Social | Constitution | Not Started | Kevin, Jaelyn, Claire, Joyce + company page
10 | Email signatures: new positioning line + tagline | Day 2 | ECHO | Brand Assets | Constitution | Not Started | All partners
11 | Proposal template: cover + first page + service overview rewrite | Day 2 | ECHO | Sales Assets | Constitution | Not Started | Taxonomy rule applied to service descriptions
12 | Service decks: all 3 service line decks rewritten (outcomes lead) | Day 3 | ECHO + Valentina | Sales Assets | Day 2 proposal template | Not Started | Leadership Intelligence / Programmes / Search & Advisory
13 | Workshop descriptions: 27 modules renamed to functional names | Day 3 | ECHO | Content | Taxonomy rule | Not Started | Framework names move to "powered by" (Level 3)
14 | Webinar landing page template: new positioning + 3-layer framing | Day 3 | ECHO + Valentina | Content | Constitution | Not Started | Template for all future webinars
15 | Newsletter header + format update | Day 3 | ECHO + Carl | Content | Constitution | Not Started | Leadership Intelligence Brief
16 | Board Brief template update | Day 3 | Hans + ECHO | Content | Constitution | Not Started | New positioning + taxonomy
17 | NEXUS: endorsed brand messaging audit + "NEXUS by LYC" tightened | Day 4 | James + Emily | Product | Constitution | Not Started | All NEXUS surfaces checked
18 | NEXUS: in-app handoff triggers configured | Day 4 | James + Akira | Product | Maturity model | Not Started | Content invites after first assessment, community after engagement
19 | Maturity stack: Stage 1 content sequence (first 30 days) | Day 4 | ECHO + LENS | Content | Constitution + 3-pillar strategy | Not Started | Automated invite sequence
20 | Community: first roundtable topics + invite list methodology | Day 4 | ECHO + LENS | Community | Maturity model | Not Started | First event planning
21 | All LinkedIn profiles go live (partners + consultants) | Day 5 | Carl + ECHO | Social | Day 2 copy | Not Started | Simultaneous update
22 | Podcast intro + outro rewritten | Day 5 | ECHO | Content | Constitution | Not Started | New positioning framing
23 | Outreach templates: new opening lines, lead with insight | Day 5 | Maria + Emily | Outreach | Messaging architecture | Not Started | Partner/referral + candidate templates
24 | External profiles: Pagoda + directories updated | Day 5 | Maria | Outreach | Constitution | Not Started | All directory listings
25 | Brand steward full audit of all updated assets | Day 6 | Emily | QA | All prior days | Not Started | Check against constitution + taxonomy rule
26 | Internal team briefing: new brand promise + architecture + rules | Day 6 | Emily + Kevin | Operations | Audit complete | Not Started | Team alignment session
27 | FAQ document created for team questions | Day 6 | Emily | Operations | Briefing | Not Started | Anticipate questions
28 | Final fixes from audit + briefing | Day 6 | All agents | QA | Audit findings | Not Started | Last pass before go-live
29 | Website goes live | Day 7 | Akira + Valentina | Website | Day 6 fixes | Not Started | Signal moment — no external announcement
30 | All LinkedIn profiles + company page go live simultaneously | Day 7 | Carl + ECHO | Social | Day 6 fixes | Not Started | Coordinated switch
31 | All templates switch over (proposals, decks, briefs, email sigs) | Day 7 | ECHO + Maria | Operations | Day 6 fixes | Not Started | All outbound materials use new branding
32 | First newsletter under new branding goes out | Day 7 | ECHO + Carl | Content | Day 3 newsletter update | Not Started | First public touchpoint under new brand
33 | KPI dashboard created with Day 0 baseline | Day 7 | Emily + LENS | Analytics | Day 1 baseline | Not Started | 15 metrics, 3 tiers, monthly review cadence

## Webinar #1 Tracker
WEBINAR #1 — Production Tracker
"Your China Leaders Are Not in Your Global Succession Plan" ¦ Aug 19, 2026 ¦ 10:00 AM HKT
PRODUCTION TASKS
# | Task | Owner | Deadline | Status | Dependencies | Notes
1 | Audience list segmentation by priority + channel | LENS | Aug 7 | Pending | —
2 | China Leadership Pipeline Assessment (CPI) — live | Akira + James | Aug 12 | Pending | Deck data | CRITICAL — blocks registration page
3 | Registration page — design + copy + build | Valentina + ECHO + Akira | Aug 12 | Pending | Task #2 | Goes live on Day 7 of brand rollout
4 | Teams webinar setup + share link | Kevin | Aug 8 | Pending | — | BLOCKING — Kevin action item
5 | Deck refinement — brand polish + new positioning | ECHO + Valentina | Aug 14 | Pending | Brand rollout Day 1-2
6 | Deck data points verified | Hans | Aug 12 | Pending | —
7 | Invitation email copy (updated brand) | ECHO | Aug 12 | Pending | Brand rollout Day 1-2
8 | LinkedIn promo posts (3-5 angles) | ECHO + Carl | Aug 14 | Pending | Brand rollout Day 5
9 | Newsletter feature / dedicated send | ECHO + Carl | Aug 15 | Pending | Brand rollout Day 7
10 | Outreach sequence with webinar invite | Maria | Aug 14 | Pending | Task #1
11 | Post-event email | ECHO | Aug 18 | Pending | Task #5
12 | Full production QA (all assets, all links) | Emily | Aug 18 | Pending | #2, #3, #5, #7
13 | Registration page go-live | Akira + Emily | Aug 12 | Pending | #2, #3, #4 | MILESTONE
14 | Webinar day execution + Q&A support | Emily + Kevin | Aug 19 | Pending | All | EVENT DAY
KEVIN'S ACTION ITEMS
# | Action | Deadline | Status | Notes
1 | Set up Teams webinar, share link | Aug 8 | Pending | Blocking #3 — registration page build
2 | Review + approve website copy + design | Aug 8 | Pending | Day 2 output from ECHO + Valentina
3 | Review + approve deck v2 | Aug 14 | Pending | Final deck from ECHO + Valentina
4 | Review + approve LinkedIn profile copy | Aug 10 | Pending | ECHO delivers Day 2
5 | Go-live greenlight for website | Aug 12 | Pending | Final check before Day 7 launch
6 | Webinar live delivery | Aug 19 | Pending
CTA ARCHITECTURE — consistent everywhere
1. Primary CTA: China Leadership Pipeline Assessment (5 min, instant CPI score)
2. Secondary CTA: 20-min executive briefing with Kevin
3. Tertiary CTA: Full research report download / Newsletter subscription
4. Core promise: 'Find out where your company stands on China leadership — and what to do about it.'
5. Funnel: Cold social → Webinar → Assessment → Briefing → Advisory

## Comms Methodology
Comms Methodology — Agency Pitch Framework
Phased, decision-gated approach to product communication strategy — from the NEXUS GTM process
Core Principles (5)
# | Principle | Definition
1 | Taxonomy Principle | Outcomes lead. Methods follow. Taxonomy recedes. Users should know what they're getting and why before they learn internal framework names.
2 | Decision Gates, Not Revisions | Each phase ends with a lock. Once locked, it doesn't reopen unless new information changes the underlying assumption. Prevents scope drift.
3 | Anti-Positioning First | You don't win by saying you're better. You win by changing the frame of the comparison. Define who you're positioning against and how you reframe.
4 | One Engine, Many Voices | Every core idea propagates across voices and channels. Strategy defines who says what, where, and to what end.
5 | The Product Never Speaks First | Thought leader builds the category. Product voice explains the solution. Institutional voice closes enterprise sale. Nobody feels sold to.
Phase Overview (6 Phases)
Phase | Title | What Gets Decided | Duration
1 | Brand Strategy & Positioning | Category, brand architecture, voice, tagline, visual system | 1-2 days
2 | Messaging Architecture & Content Strategy | Message layers, audience messaging, anti-positioning, content pillars, content engine, objections | 2-3 days
3 | Launch Strategy & Campaign Architecture | Launch timeline, campaign phases, content calendar, asset inventory | 1-2 days
4 | Partnerships, Ecosystem & KPI Framework | Partner strategy, ecosystem integration, pricing tiers, KPIs, measurement plan | 1-2 days
5 | Cross-Business Handoff (Optional) | How product feeds other business units (B2C→B2B, product→services) | 1 day
6 | Unified Flywheel Integration (Optional) | How product plugs into broader business flywheel — asset mapping, calendar, new North Star | 1 day
Common Pitfalls to Avoid (6)
Pitfall | Why It's a Problem
Skipping Phase 1 | Everyone wants to talk about launch tactics. Positioning is 80% of the work. Get it right first.
Doing everything in one meeting | The brain can only absorb so much. One phase at a time. One decision at a time.
Revisiting locked decisions | "I just had another idea" is not new information. New competitor or market data? That's a reason.
Leading with taxonomy | Resist showing off frameworks and clever names. Audience doesn't care what you call it. They care what it does.
Forgetting anti-positioning | Every category has incumbents. If you don't define how you're different, people default to price and features.
No North Star metric | If you don't know what winning looks like, you'll never know if you won. Pick one thing. Measure it obsessively.
Application to LYC Brand Rollout
Methodology Element | How It's Applied in Rollout | Owner
Taxonomy Principle | All content leads with outcomes (what you get), not framework names. ECHO enforces across all assets. | ECHO
Decision Gates | Each Phase of the brand rollout has explicit lock points. Kevin signs off before moving forward. | Kevin
Anti-Positioning | LYC positions against legacy retainer search firms — frame reframed as intelligence vs. staffing. | Kevin / ECHO
One Engine, Many Voices | 4 LinkedIn profiles (Kevin/Claire/Jaelyn/Joyce) share one thesis, each from a different angle. | ECHO
Product Never Speaks First | Kevin's thought leadership builds the category first; Claire's product content explains solutions. | Kevin / Claire
6-Phase Model | LYC brand rollout follows the same 6 phases, compressed into a 1-week sprint with decision gates. | Emily
North Star Metric | Webinar #1 registrations (Aug 19) serve as the launch-phase North Star. | LENS

## NEXUS Board Strategy Comm
NEXUS Board — Strategy Communication Tracker
Tracks board-level decisions and communication for NEXUS strategy rollout
# | Task | Owner | Deadline | Status | Notes
SEC
1 | Board strategy review meeting | Board + Kevin | TBD | Pending | Board review of NEXUS strategy direction
2 | Board approval of strategy pivot | Board | TBD | Pending | Formal board approval for strategy changes
3 | Board communication to NEXUS team | Board + Kevin | TBD | Pending | How strategy is communicated to the NEXUS team
4 | Board communication to investors | Board + Kevin | TBD | Pending | Investor-facing strategy update
5 | Board communication to market | Board + Maria/ECHO | TBD | Pending | External market-facing strategy announcement
EXEC
6 | Brand rollout alignment with board strategy | Emily + Kevin | Aug 12 | In Progress | Ensure brand rollout is consistent with board-approved strategy
7 | NEXUS product roadmap alignment | James + Board | TBD | Pending | Product roadmap reflects strategy direction
8 | KPIs / success metrics alignment | LENS + Board | TBD | Pending | Define what success looks like post-strategy
RISK
9 | Risk assessment of strategy shift | Hans + Board | TBD | Pending | Identify risks in strategy communication and execution
10 | Client communication plan | Maria + Board | TBD | Pending | How to communicate strategy changes to clients

## Feishu Files
# | Document Name | Type | Feishu Link | Category | Content Pillar | Status | Notes
1 | Content Pillars Aligned v3 | Sheet | https://l5tf5m43wr.feishu.cn/sheets/VDkPsNGEwhmLa4tqA9pcatHNnEh | Content Calendar | All 3 Pillars | Current | Master calendar - 3 webinars/mo + workshops by pillar
2 | Headline-First System v2 | Sheet | https://l5tf5m43wr.feishu.cn/sheets/OBsMsiX4ThazS1t3ZveczT9inrh | Content System | All 3 Pillars | Current | 15 hooks x 3 formats (long/short/reel)
3 | Week 1 Scripts v2 | Doc | https://l5tf5m43wr.feishu.cn/docx/D2dBdUYMyoIaJSxwULvcR4cFnkd | Scripts | All 3 Pillars | ECHO v4.0 compliant | 45 scripts (15 hooks x 3), ~22,403 words
4 | Series A v7 | Doc | https://l5tf5m43wr.feishu.cn/docx/Jq8wdU4xloiJAmxHy1wcIDp4n7d | Scripts | Career | Complete | 18 hooks, 54 scripts
5 | Series B v8 | Doc | https://l5tf5m43wr.feishu.cn/docx/VYcZdgCOCoh6hgxQjRFc8lvKnjd | Scripts | Career | Tone revised | 24 hooks, 72 scripts
6 | Series C Hook Map v7 | Doc | https://l5tf5m43wr.feishu.cn/docx/LvWqd4514oBRK7xKmx4c3dX9nZe | Hook Map | China & Leadership | Complete | 25 hooks, 5 clusters
7 | Series C Sample Scripts v9 | Doc | https://l5tf5m43wr.feishu.cn/docx/ZuCIdAQEDoyeiQxmwoGcdXtanJV | Scripts | China & Leadership | 4 samples done | 4 sample scripts; full 75 pending
8 | Series D Hook Map v10 | Doc | https://l5tf5m43wr.feishu.cn/docx/VpFJdD1iQoPO9Lxt86Ic8QKpn4e | Hook Map | AI & Leadership | Complete | 25 hooks, 5 clusters
9 | Series D Sample Scripts v10 | Doc | https://l5tf5m43wr.feishu.cn/docx/VabodDdjJo9eO8xRGFEcrFe6nbc | Scripts | AI & Leadership | 4 samples done | 4 sample scripts; full 75 pending
10 | Content Calendar v1 (legacy) | Sheet | https://l5tf5m43wr.feishu.cn/sheets/XgKrsJNJyhiq6At2ebxc62IAnFR | Content Calendar | All | Superseded by v3 | Original calendar before pillar alignment
12 | WAVE BRD v1.0 | Doc | https://l5tf5m43wr.feishu.cn/docx/NsrodeH2doEWwMx67fCcT8Xtncc | App Spec | WAVE | Current | Business Requirements Document - 8 modules, 87 tickets
13 | WAVE Development Tickets v1.0 | Doc | https://l5tf5m43wr.feishu.cn/docx/OLuLdFDWdofvXzxRYCWce2gXnGd | App Spec | WAVE | Current | 87 dev tickets with priority/effort/deps
14 | WAVE Intelligence Layer Spec v1.0 | Doc | https://l5tf5m43wr.feishu.cn/docx/AqQSdPFxMoXmsyx1LRbcVqAgnqb | App Spec | WAVE | Current | Intelligence module specification
15 | LYC Intelligence Design Spec | Doc | https://l5tf5m43wr.feishu.cn/docx/JaczdojEQo7NCBxeoqJco2Ylnod | App Spec | WAVE | Current | Intelligence design specification
16 | Outreach Funnel Refined v2 | Doc | https://l5tf5m43wr.feishu.cn/docx/KNjedt5jsoUWkfxF7Q1cJL8jnuf | App Spec | WAVE | Current | Outreach funnel v2 refined spec
17 | Outreach Funnel Mapping Spec | Doc | https://l5tf5m43wr.feishu.cn/docx/PyYPdvoj5oy80FxZgPOcpUhNn5d | App Spec | WAVE | Current | Outreach funnel mapping specification
18 | WAVE DB Schema - Outreach Funnel | Doc | https://l5tf5m43wr.feishu.cn/docx/CcQTdIh8FoO5YqxKpUXcvSS4n5b | App Spec | WAVE | Current | Database schema SQL for outreach funnel
19 | WAVE Project PM Tracker | Sheet | (uploaded file - GaHfbAhjPoF0Z5xUX49ca0mLnnM) | PM | WAVE | Current | 87 tickets with status/priority/module tracking
20 | WAVE Business Spec Pitch ICP | Slides | (uploaded file - Qye0bsFr5oNzEDx6Oq4c8gnunHg) | Presentation | WAVE | Current | Business pitch deck for ICP
21 | ECHO Asset Master v6.0 | Doc (Notion) | https://lyc-partners.notion.site/ECHO-Asset-Master-v6-0-Source-of-Truth-2026-08-04-3b2fafae51be81aeb291ec9c33e67faa | Brand Compliance | Echo | Source of Truth | Brand compliance source of truth - designated by Kevin 2026-08-04
21 | Social Content Tracker v1 | File (xlsx) | https://l5tf5m43wr.feishu.cn/file/Nmu4bW4SCoxjjcxMo5pca1N3nPg | Social Media | All 3 Pillars | Active | 18 tasks x 4 voices x 3 platforms + format playbook + weekly cadence
21 | Carl Agent Spec v2.0 | Docx | https://l5tf5m43wr.feishu.cn/docx/FAdydmo4FosxDSxT9vTcLMQpnph | Agent Specs | N/A | Current | Updated to reflect dual role: WAVE build + Content/Flywheel ops
22 | Social Content Tracker v1.1 | Excel (file) | https://l5tf5m43wr.feishu.cn/file/ZFgAbmdwwoPfbZxKj5JcKpZLnIh | Content Operations | All 3 Pillars | Current | 5 sheets — tracker, format playbook, voice matrix, weekly cadence, summary. 26 tasks, 17 formats, 4 voices + Emily ops
23 | Social Content Operations Playbook v1.1 | Docx (file) | https://l5tf5m43wr.feishu.cn/file/Awl4bydJIo6rQdxs7hAcBD8zn7N | Content Operations | All 3 Pillars | Current | Full social strategy — 3 platforms, 4 voices, 17 formats, 7-dimension brand guardrails, repurposing pyramid, B2B differentiation research integrated
24 | Emily — Social Content Onboarding Guide | Docx (file) | https://l5tf5m43wr.feishu.cn/file/P8mzbaZFYofCaMxNU0bck7Oynae | Content Operations | All 3 Pillars | Current | Onboarding guide for Emily — role scope, deliverables, brand guardrails, weekly rhythm, quality checklist, first-week action plan
25 | Carl Agent Spec v2.0 | Docx | https://l5tf5m43wr.feishu.cn/docx/FAdydmo4FosxDSxT9vTcLMQpnph | Agent Spec | N/A | Current | Dual role: WAVE build + Content/Flywheel operations. 10 chapters.

## Notion Pages
# | Page / Database Name | Notion ID | Category | Owner | Purpose | Status
1 | Nexus Profile | 277fafae | Agent Config | NEXUS | Agent identity & behavior (READ ONLY) | Live
2 | Task Tracker | af9cb54a | Execution | NEXUS | Execution truth - all tasks | Live
3 | Strategic Streams | df5747f2 | Planning | NEXUS | Roadmap & prioritization | Live
4 | AI Flight Log | 241a44ed | Logging | NEXUS | Effort & throughput logging | Live
5 | Build Bible | a2c05a1d | Technical | NEXUS | Build specifications & architecture | Live
6 | LYC Constellation | 32dfafae | System Map | NEXUS | System ecosystem map | Live
7 | Master System Documentation | 2b449f74 | SOPs | NEXUS | SOPs, session documentation | Live
8 | Talent Book | 46f6e434abf542618d2e83ec518926ff | CRM | NEXUS/DEX | Talent relationship management | Live
9 | Candidate Tracker | 348fafae-51be-8173-... | Pipeline | NEXUS/DEX | Active candidate pipeline | Live
10 | Business Proposal | f08fd5d81b064f24a0eb7c8116372ca2 | Deals | NEXUS | Deal/proposal management | Live
11 | Project Overview | 227cfd12c7534d6398301152051ecb6c | Projects | NEXUS | High-level project status | Live
12 | Webinar 1 Deck - China Leadership Gap | 39bfafae51be810ea92ae396930895ea | Webinar Deck | Carl | Slide deck for China pillar webinar | Ready
13 | Webinar 1 Ops Pack | 39bfafae51be811b8762c02c6a3319f9 | Webinar Ops | Carl | Invitation + follow-up + registration | Ready
14 | Webinar 2 Deck - Partnership Deficit | 39bfafae51be816aa5cbffe1ba4c8d2d | Webinar Deck | Carl | Slide deck for Force 2 webinar | Ready
15 | Webinar 2 Ops Pack | 39bfafae51be8126b66fe57f60dd500a | Webinar Ops | Carl | Registration + follow-up | Ready
16 | Webinar 3 Deck - Succession Illusion | 39bfafae51be81f19086f6f2d9fd6fe3 | Webinar Deck | Carl | Slide deck for Force 3 webinar | Ready
17 | Webinar 3 Ops Pack | 39bfafae51be81328084f17b84e570f2 | Webinar Ops | Carl | Registration + follow-up | Ready
18 | Webinar 4 Deck - Integrated Forum | 39bfafae51be81ac9091e48aa774f927 | Webinar Deck | Carl | Overview/pitch webinar | Ready
19 | Webinar 4 Ops Pack | 39bfafae51be8150a3b1fd160e28b861 | Webinar Ops | Carl | Registration + follow-up | Ready
20 | Webinar Slide Master & Brand | 39bfafae51be815e934ec075e7355a67 | Template | Carl | Visual standards for all webinar decks | Ready
21 | Workshop 1 Deck - China Exposure (Force 1) | 39bfafae51be81429149d2f37237f987 | Workshop Materials | Carl | Main presentation deck | Ready
22 | Workshop 1 Facilitator Guide | 39bfafae51be818fb3f8c3d6be4c1e46 | Workshop Materials | Carl | Step-by-step facilitation instructions | Ready
23 | Workshop 1 Participant Workbook | 39bfafae51be8153a08ec48bdb15a210 | Workshop Materials | Carl | Exercises and worksheets | Ready
24 | Workshop 1 Registration & Ops | 39bfafae51be81a58dd5ed8924ddd694 | Workshop Ops | Carl | Logistics, registration, scheduling | Ready
25 | Workshop 2 Deck - Partnership Dynamics | 39bfafae51be813a9fefd6be604938e9 | Workshop Materials | Carl | Main presentation deck | Ready
26 | Workshop 2 Workbook & Facilitator Guide | 39bfafae51be8143976bc221fa777cb8 | Workshop Materials | Carl | Combined guide | Ready
27 | Workshop 2 Registration & Ops | 39bfafae51be81fe9758c50aa3463a54 | Workshop Ops | Carl | Logistics, registration, scheduling | Ready
28 | Workshop 3 Deck - Succession Audit (Force 3) | 39bfafae51be81e8bbfaf93b0f56de5d | Workshop Materials | Carl | Main presentation deck | Ready
29 | Workshop 3 Workbook & Facilitator Guide | 39bfafae51be81ebbfe1c345a332c2c | Workshop Materials | Carl | Combined guide | Ready
30 | Workshop 3 Registration & Ops | 39bfafae51be81dba1cae045b0e462ee | Workshop Ops | Carl | Logistics, registration, scheduling | Ready

## Supabase Tables
# | Table Name | Ownership | Category | Purpose | Key Fields | Status
1 | events | Carl (owned) | Events | Events master - webinars, workshops, training | id, title, type, status, scheduled_at, capacity, pillar | Active
2 | event_registrations | Carl (owned) | Events | Event sign-ups, attendance, feedback | id, event_id, contact_id, status, attended, feedback_score | Active
3 | event_waitlist | Carl (owned) | Events | Waitlist management for oversubscribed events | id, event_id, contact_id, position, notified | Active
4 | training_programs | Carl (owned) | Training | Multi-session training curricula definitions | id, name, description, sessions_count, price, pillar | Active
5 | training_enrollments | Carl (owned) | Training | Training enrollment & progress tracking | id, program_id, contact_id, status, progress_pct, payment_status | Active
6 | vista_contacts | VISTA (read) | Contacts | Contact records for event registration | id, name, email, company, title, signal_score | Read-only
7 | products | WAVE/Echo (read) | Catalog | Product catalog linked to campaigns | id, name, type, price, description | Read-only
8 | content_assets | WAVE/Echo (read) | Content | Content pipeline assets | id, title, type, pillar, status, url | Read-only
9 | campaigns | WAVE/Echo (read) | Marketing | Marketing campaigns linked to events | id, name, type, status, start_date, end_date | Read-only
10 | build_tracker | WAVE (shared) | Dev | Development task tracking (291 tasks) | id, task, status, priority, assignee, sprint | Read-only
11 | email_sequences | WAVE/Echo (shared) | Comms | Email sequence definitions (26 sequences) | id, name, type, steps_count, status | Read-only
12 | assets | WAVE (shared) | Resources | Resource files (132 assets) | id, name, type, url, size | Read-only

## Apps & Platforms
# | App / Platform | URL | GitHub Repo | Owner | Purpose | Status
1 | WAVE | https://wave-seven.vercel.app | kevinhongfr-star/Wave | Carl / NEXUS | Content ops - calendar, distribution, assets, analytics, agents | Phase 0 Live
2 | VISTA | https://vista-azure-delta.vercel.app | kevinhongfr-star/vista | VISTA (James) | BD & market intelligence dashboard | v9.7 Live
3 | DEX AI | https://dex-ai-nine.vercel.app | - | NEXUS/DEX | Assessment engine - TRIDENT scoring, candidate eval | Live
4 | LYC Intelligence (B2C) | https://lyc-intelligence.app | kevinhongfr-star/lyc-intelligence | NEXUS | Council/events frontend for end-users | In development
5 | LYC Website | https://website-weld-pi-13.vercel.app | - | Valentina | Corporate website | Existing
6 | Notion Workspace | https://www.notion.so/lyc-partners | - | NEXUS | Canonical data layer - CRM, tasks, specs, docs | Live
7 | Feishu Workspace | https://l5tf5m43wr.feishu.cn | - | NEXUS/Carl | China-side comms, docs, sheets, collaboration | Live
8 | Supabase (WAVE DB) | Supabase project | - | WAVE/Carl | Backend database - events, contacts, campaigns | Live

## Specs & Documents
# | Spec / Document Name | Category | Owner | Purpose | Location | Status
1 | SOUL.md (Agent Soul & OS) | Identity | NEXUS | Agent identity, behavior protocols, writing rules | Agent workspace | Active
2 | ECHO v4.0 Spec | Content System | NEXUS/Carl | Content production - tone, banned words, structure | Notion + workspace | Active
3 | LYC Writing Master Rules v2.0 | Content System | NEXUS/Carl | Tone, banned words, double-layer principle, 9-test checklist | Notion | Active
4 | Headline-First Hook System v2 | Content System | NEXUS/Carl | News-hook to YouTube script methodology | Feishu Sheet | Active
5 | CARL Automation Spec v1 | Automation | Carl | Automation specification for Carl event workflows | Local file | Complete
6 | CARL Density Clustering Report v1/v2 | Analytics | Carl | Contact density clustering analysis | Local file | Complete
7 | CARL Cross-Cluster Mapping Report v1 | Analytics | Carl | Cross-cluster contact mapping | Local file | Complete
8 | CARL Strategic Priority DeepDive v1 | Strategy | Carl | Strategic priority deep-dive for program assignment | Local file | Complete
9 | CARL Subsegmentation Report v1 | Analytics | Carl | Contact subsegmentation analysis | Local file | Complete
10 | TRIDENT Scoring Protocol | Assessment | NEXUS/DEX | Candidate evaluation (40/30/20/10 split) | Notion | Active
11 | CANVAS Profiling Framework | Assessment | NEXUS/DEX | Deep candidate profiling | Notion | Active
12 | Internal Portal Full Spec | Technical | NEXUS | 27-route internal portal architecture | Notion | In development
13 | WAVE Development Tickets | Technical | NEXUS/Carl | Dev tickets for WAVE app build | Notion + GitHub | Ongoing
14 | LYC Business Specs (BRD, ICP) | Business | NEXUS | BRD, ICP, engagement models | Notion | Active
15 | CARL Full Inventory (Markdown) | Reference | Carl | Complete asset inventory (processes, scope, links) | Local .md | Active
16 | CARL Supabase Tables Spec (Markdown) | Reference | Carl | DB table schemas, workflows, API, cron jobs | Local .md | Active
18 | WAVE BRD v1.0 | App Spec | NEXUS/Carl | Marketing ops platform requirements - 8 modules | Feishu | Current
19 | WAVE Development Tickets v1.0 | App Spec | NEXUS/Carl | 87 tickets (P0-P2) across 8 modules, ~120h total | Feishu | Current
20 | WAVE Intelligence Layer Spec v1.0 | App Spec | NEXUS/Carl | Intelligence/analytics module spec | Feishu | Current
21 | LYC Intelligence Design Spec | App Spec | NEXUS/Carl | Intelligence design specification | Feishu | Current
22 | WAVE Outreach Funnel Specs | App Spec | NEXUS/Carl | Outreach funnel v2 + mapping + DB schema | Feishu | Current
23 | WAVE PM Tracker | PM Tracker | NEXUS/Carl | 87 tickets with status/priority/module tracking | Feishu | Current
24 | ECHO Asset Master v6.0 | Brand Compliance | Echo/Kevin | Source of truth for Echo brand compliance | Notion | Source of Truth
24 | Social Content Operations Playbook (in tracker) | 12 formats x 4 voices x weekly cadence | Carl | https://l5tf5m43wr.feishu.cn/file/Nmu4bW4SCoxjjcxMo5pca1N3nPg | Active | LinkedIn/Instagram/YouTube Shorts strategy
25 | Social Content Operations Playbook v1.1 | Content Operations | Carl | Full social strategy across 3 platforms, 4 voices, 17 formats | Feishu + Local | Active
26 | Emily Social Content Onboarding Guide | Content Operations | Carl | Onboarding guide for content ops lead | Feishu + Local | Active
27 | Carl Agent Spec v2.0 | Agent Identity | Carl | Dual role definition: WAVE build + Content/Flywheel ops | Feishu + Local | Active

## Content Pipeline
# | Series | Perspective | Content Pillar | Total Hooks | Scripts Done | Scripts Total | Feishu Link | Status
1 | Series A (v7) | I've lived this | Career | 18 | 54 | 54 | https://l5tf5m43wr.feishu.cn/docx/Jq8wdU4xloiJAmxHy1wcIDp4n7d | Complete
2 | Series B (v8) | I've watched from the chair | Career | 24 | 72 | 72 | https://l5tf5m43wr.feishu.cn/docx/VYcZdgCOCoh6hgxQjRFc8lvKnjd | Tone revised
3 | Series C (v9) | I've placed them across both worlds | China & Leadership | 25 | 4 | 75 | https://l5tf5m43wr.feishu.cn/docx/LvWqd4514oBRK7xKmx4c3dX9nZe | Hook map + 4 samples
4 | Series D (v10) | I see who's ready | AI & Leadership | 25 | 4 | 75 | https://l5tf5m43wr.feishu.cn/docx/VpFJdD1iQoPO9Lxt86Ic8QKpn4e | Hook map + 4 samples
5 | Week 1 v2 (cross-series) | Mixed | All 3 Pillars | 15 | 45 | 45 | https://l5tf5m43wr.feishu.cn/docx/D2dBdUYMyoIaJSxwULvcR4cFnkd | ECHO v4.0 compliant
6 | Headline-First System v2 | Mixed | All 3 Pillars | 15 | - | - | https://l5tf5m43wr.feishu.cn/sheets/OBsMsiX4ThazS1t3ZveczT9inrh | Active
7 | Social Content (Multi-platform) | Podcast/webinar repurpose + original | All 3 Pillars | 12 formats | 0 | ~15 posts/week target | https://l5tf5m43wr.feishu.cn/file/Nmu4bW4SCoxjjcxMo5pca1N3nPg | Just started - v1 tracker live
8 | Social Content — LinkedIn 4 Voices | 4-voice triangulation | All 3 Pillars | N/A | N/A | N/A | https://l5tf5m43wr.feishu.cn/file/ZFgAbmdwwoPfbZxKj5JcKpZLnIh | Onboarding — Week of Aug 11 start
9 | Social Content — Instagram | Editorial premium aesthetic | All 3 Pillars | N/A | N/A | N/A | N/A | Starting with Kevin/brand account
10 | Social Content — YouTube Shorts | Repurposing layer only | All 3 Pillars | N/A | N/A | N/A | N/A | 3-4/week — search-optimized, from long-form only

## Local Files
# | File Name | Category | Purpose | Path
1 | webinar_definitions.json | Event Data | 29 industry x geo webinar cluster definitions | /app/data/sessions/session/
2 | webinar_programs.json | Event Data | Program definitions with matching rules, tier assignments | /app/data/sessions/session/
3 | CARL_Automation_Spec_v1.md | Spec | Automation specification for Carl workflows | /app/data/sessions/session/
4 | CARL_Density_Clustering_Report_v1.md | Report | Contact density clustering analysis | /app/data/sessions/session/
5 | CARL_Density_Clustering_Report_v2.md | Report | Updated density clustering | /app/data/sessions/session/
6 | CARL_Cross_Cluster_Mapping_Report_v1.md | Report | Cross-cluster contact mapping | /app/data/sessions/session/
7 | CARL_Strategic_Priority_DeepDive_v1.md | Report | Strategic priority deep-dive | /app/data/sessions/session/
8 | CARL_Subsegmentation_Report_v1.md | Report | Contact subsegmentation analysis | /app/data/sessions/session/
9 | LYC_Content_Pillars_Aligned_v2.xlsx | Calendar | Source Excel for Feishu Content Pillars v3 | /app/data/sessions/session/
10 | LYC_WEEK1_SCRIPTS_V2_FULL.md | Scripts | Week 1 v2 complete scripts (~22,403 words) | /app/data/sessions/session/
11 | headline_scripts_v2_final.json | Scripts | Week 1 v2 scripts JSON | /app/data/sessions/session/
12 | LYC_YOUTUBE_SCRIPTS_V7_ALL_18_HOOKS_COMPLETE.md | Scripts | Series A complete scripts | /app/data/sessions/session/
13 | LYC_YOUTUBE_V8_TONE_REVISED.md | Scripts | Series B complete scripts | /app/data/sessions/session/
14 | LYC_YOUTUBE_HOOK_MAP_V7_BEYOND_HEADLINES.md | Hook Map | Series C hook map | /app/data/sessions/session/
15 | LYC_YOUTUBE_HOOK_MAP_V10_AI_CAREER.md | Hook Map | Series D hook map | /app/data/sessions/session/
16 | CARL_Full_Inventory.md | Reference | Complete Carl asset inventory (Markdown) | /app/data/sessions/session/
17 | CARL_Supabase_Tables_Spec.md | Reference | Supabase table specs + workflows | /app/data/sessions/session/
19 | WAVE_Project_PM_Tracker.xlsx | PM Tracker | WAVE project management - 87 tickets with status | /app/data/sessions/session/
20 | WAVE_Project/Business_Specs/ | App Spec | WAVE business specs (BRD, tickets, intelligence, funnel) | /app/data/sessions/session/
21 | WAVE_Project/Database_Schema/ | DB Schema | Outreach funnel SQL schema | /app/data/sessions/session/
22 | WAVE_Project/wave-app/ | Source Code | Next.js source code for WAVE app (Phase 0) | /app/data/sessions/session/
22 | LYC_Social_Content_Tracker_v1.xlsx | Social Media Tracker | ./
23 | LYC_Social_Content_Tracker_v1.1.xlsx | Content Operations | Social content tracker — 5 sheets, 26 tasks, 17 formats | /app/data/sessions/session/
24 | social_content_playbook_v1.1.docx | Content Operations | Full social playbook v1.1 with B2B differentiation research | /app/data/sessions/session/
25 | emily_social_content_onboarding.docx | Content Operations | Emily onboarding guide | /app/data/sessions/session/
26 | carl_agent_spec_v2.docx | Agent Identity | Carl agent spec v2 — dual role (WAVE + content ops) | /app/data/sessions/session/

## Revenue Model
# | Revenue Stream | Price | Frequency | Pax/Session | Monthly Revenue | Start | Notes
1 | Webinar (free funnel) | Free | 3/month total | - | $0 (lead gen) | Immediate | Feeds into workshops
2 | China & Leadership Workshop | $150 / 1000RMB pax | 3/month | 5-15 pax | $450-$1,350 | Immediate | Paid, highest volume
3 | Career Workshop | $150 / 1000RMB pax | 2/month | 5-15 pax | $300-$900 | Immediate | Paid
4 | AI & Leadership Workshop | $150 / 1000RMB pax | 1/month | 5-15 pax | $150-$450 | Oct 2026 | Paid, starts later
5 | Diagnostic Session | $1,000/session | As needed | 1:1 | Variable | Ongoing | Post-workshop upsell
6 | Executive Search | Project fee | Signal-triggered | - | Variable | Ongoing | Highest value per deal
|  |  |  | TOTAL (workshops) | $900-$2,700 (Oct+) |  | $750-$2,250 (Aug-Sep)
|  |  |  | 6-MO TOTAL | $8,100-$24,300 |  | Plus diagnostics + exec search